## Tasks and Timeline
Sauce & Spoon Project Plan
Order | Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
Order | [7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Meeting with stakeholders |  |  |  | 1 hour
2.1 | Define SMART goals of the project |  |  |  | 1 day
2.2 | Align and evaluate stakeholders |  |  |  | 3 days
2.3 | Create project charter |  |  |  | 2 days
2.4 | Meeting witth staff to introduce the idea |  |  |  | 2 hours
2.5 | Milestone: Kick off meeting |  |  |  | 1 hour
3 | Review project documents |  |  |  | 1 day
4.1 | Research tablet models |  |  |  | 1 day
4.2 | Test tablet capability |  |  |  | 1 day
4.3 | Sign contract with menu tablet supplier |  |  |  | 1 day
4.4 | Purchase and receive tablets |  |  |  | 11 days
4.5 | Milestone: Tablets received
5.1 | Quote electricians to build necessary electrical adaptations |  |  |  | 1 day
5.2 | Decide among quotations provided and schedule instalation |  |  |  | 2 hours
5.3 | Electrical instalations to receive tablets |  |  |  | 6 days
5.4 | Quote companies to improve Wi-fi network |  |  |  | 1 day
5.5 | Decide among quotation provided and schedule adptations |  |  |  | 2 hours
5.6 | Internet network instalations |  |  |  | 2 days
5.7 | Milestone: Infraestructure ready for tablet menu
6.1 | Revamp menu |  |  |  | 5 days
6.2 | Decide items to have coupons on the menu |  |  |  | 1 day
6.3 | Decide value of the coupons |  |  |  | 1 day
6.4 | Mock-up tablet design |  |  |  | 3 days
6.5 | Load interface of tablets to look like hardcopy menus |  |  |  | 5 hours
6.6 | Prepare a survey |  |  |  | 2 days
6.7 | Integrate survey in tablets system |  |  |  | 1 day
6.8 | Integrate tablets with systems already in use |  |  |  | 3 days
6.9 | Instal tablets in their location |  |  |  | 2 days
6.11 | Milestone: Tablets ready to run pilot test
7.1 | Preparations for training |  |  |  | 7 days
7.2 | Train key staff members |  |  |  | 3 hours
7.3 | Train BOH and FOH staff |  |  |  | 2 days
8.1 | Schedule test run with friends and family |  |  |  | 3 hours
8.2 | Milestone: Run pilot tests in controlled sample group to discover any issue |  |  |  | 5 days
8.3 | Fix any issue that had arose |  |  |  | 3 days
9.1 | Shedule a date for official launching |  |  |  | 2 hours
9.2 | Announce a promotion in regular chanels |  |  |  | 1 day
9.3 | Update social media with the news |  |  |  | 3 days
9.4 | Milestone: Lauch tablet menu

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Purchase and receive tablets | Seydou informed delay on new model tablets due to storms and old models are available in the nearest warehouse | 11 | 7 days | 11 days | 21 days | M
Electrical instalations to receive tablets | How busy is the restaurante may influence | 6 | 4 days | 6 days | 8 days | M
Revamp menu | This task coming from Carter has a historic of unpredictability | 5 | 10 hours | 4 days | 7 days | L
Integrate tablets with systems already in use | Seydon informed many unkown variables, including the possibility of depending on outsource | 3 | 4 hours | 2 days | 5 days | L
Train key staff members | Difficulties may arise, but unlikely | 2 hours | 2 hours | 3 hours | 6 hours | H
Train BOH and FOH staff | It's difficult to predict how fast staff is going to get used to the new system | 2 | 3 hours | 2 days | 4 days | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Step-by-step guide to tabletops tablets for bars | https://www.buzztime.com/business/blog/step-by-step-guide-to-tabletop-tablets-for-bars/ | 2023-02-24
10 Restaurant tablets best practices | https://climbtheladder.com/10-restaurant-tablet-best-practices/ | 2023-02-24

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | Average ticket time of 8 minutes for apetizzers and 12-15 minutes for entrees | Are customers receiving the correct orders? | Guests using tablets receive their order correctly in 98% of the cases | FALSE
Tablest are easy-of-use | Reduction by 30 minutes in average table turn. | Are customers having a better dinner experience? | Customers that used tablets responded 80% more survey than customer attended traditionally | FALSE
Tablets are functional | 1 min time for checking out | Do all the tablets work as expected? | Customers that used tablets were 50% more positive in surveys answered | FALSE
| Less then 5% of customer using tablets report technical issues | How quickly are customer learning how to navigate the tablet? | Only 1 issue of functionality is reported per week | FALSE
| 98% of accuracy in orders |  |  | FALSE
| Customer wait time in the lobby inferior to 10 minutes |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time of 8 minutes for apetizzers and 12-15 minutes for entrees | Are customers receiving the correct orders? | Guests using tablets receive their order correctly in 98% of the cases | Have you used the new tablet order system in Sauce and Spoon restaurant? | Yes/No | Yes | No
Reduction by 30 minutes in average table turn. | Are customers having a better dinner experience? | Customers that used tablets responded 80% more survey than customer attended traditionally | Have you received your order correctly in the first attempt? | Yes/No | Yes | No
1 min time for checking out | Do all the tablets work as expected? | Customers that used tablets were 50% more positive in surveys answered | On a scale of 1-5, 1 being Very Confusing, and 5 being Very simple, how do you classify your experience using a tablet to order? | Scaled | 1 | 2 | 3 | 4 | 5
Less then 5% of customer using tablets report technical issues | How quickly are customer learning how to navigate the tablet? | Only 1 issue of functionality is reported per week | How long did you wait to be sitted? | Multiple choice | Immediately | 0-5 minutes | 5-10 minutes | 10-15 minutes | Over 15 minutes
98% of accuracy in orders |  |  | Would you recommend Sauce and Spoon to a friend? | Yes/no | Yes | No
Customer wait time in the lobby inferior to 10 minutes |  |  | Did you check out through the tablet system? | Yes/No | Yes | No
|  |  | Did you experienced any issues while using the tablet? Please, if your answer is positive, state breafly what happened. | Open-ended | Open-ended
|  |  | How long did take to you receive your order? | Multiple choice | Less than 5 minutes | 5-10 minutes | 10-15 minutes | 15-20 minutes | Over 20 minutes
|  |  | Did you like the options offered in coupons? | Yes/No | Yes | No
|  |  | You can make any comment about your experience in Sauce and Spoon Restaurant. | Open-ended | Open-ended